## Preparation
Step | Date | Time | Task Description | Responsible | Status | Completed | Comments
Date
1 |  |  | Application Preparation
2 |  |  | Determine full list of applications on the server | DBA |  |  | The SQL Server may not be a dedicated server or there may be supporting applications that have been installed on the server. Identify any component that needs installed. Below are some examples.
3 |  |  | Application Name (Apps that provide drivers, IIS, supporting applications, apps that share the server with SQL Server) | DBA |  |  | Enter the Location to the Install Application and the Setup instructions document in this cell.
4 |  |  | Application Name (Antivirus Software) | DBA |  |  | Enter the Location to the Install Application and the Setup instructions document in this cell.
5 |  |  | Other applications (Editors, WinZip, FTP applications, etc.) | DBA |  |  | Place the Link to the Install Application and the Setup instructions document in this cell.
6 |  |  | Server Preparation
7 |  |  | Note Server IP Address | DBA |  |  | Enter the Server's IP Address 000.000.000.000
8 |  |  | Note Drive Letters on SQL Server | DBA |  |  | Note Drive letters. Note the drive where data, logs, and backups are stored.
9 |  |  | Note Licensing of SQL Server | DBA |  |  | Processor License for number of processors / Per User - note number of users
10 |  |  | Note SQL Server Configuration | DBA |  |  | Document SQL Server configuration. Usually, it is not the default.
11 |  |  | Note number of processors on the SQL Server | DBA |  |  | Document the number of processors on the Server
12 |  |  | Get SQL Server CD | DBA |  |  | Verify the location of the SQL Server Install CD
13 |  |  | Download SQL Server latest Service Pack | DBA |  |  | Download the latest Service Pack and note the location.
14 |  |  | Download Feature Pack | DBA |  |  | Download the Feature pack and note the location. URL for Feature Pack - http://www.microsoft.com/downloads/details.aspx?familyid=50B97994-8453-4998-8226-FA42EC403D17&displaylang=en
15 |  |  | SSIS / DTS Preparation
16 |  |  | Determine full list of DTS on the server | DBA |  |  | Identify DTS packages that are out of service
17 |  |  | Determine full list of SSIS Packages on the server | DBA |  |  | Identify SSIS packages that are out of service
18 |  |  | Mapping Databases Preparation
19 |  |  | Map Applications to Databases | DBA |  |  | Create a spreadsheet of applications and supporting databases
20 |  |  | Map DTS Packages to databases | DBA |  |  | Create a spreadsheet of DTS packages and supporting databases
21 |  |  | Map SSIS Packages to databases | DBA |  |  | Create a spreadsheet of SSIS packages and supporting databases
22 |  |  | Map Reports to databases | DBA |  |  | Create a spreadsheet of Reports and supporting databases
23 |  |  | Identify Testers for all affected applications, SSIS and DTS packages
24 |  |  | Identify Groups that own applications that touch the SQL Server. | DBA
25 |  |  | Communicate Application list to Business departments, Application Development, and any other group that may own applications that touch the SQL Server. Get feedback from these groups. | DBA
26 |  |  | Meet with Business Unit, Application Development, Network, DBAs to put create a contact list, determine time and date of the upgrade, applications that will be affected, and the method of communication. | DBA
27 |  |  | Identify Testers for all affected applications | Business Unit |  |  | The Business unit will be the best one to identify testers for its applications. Get the tester's name and phone number.
28 |  |  | Identify Testers for all affected DTS packages | DBA
29 |  |  | Identify Testers for all affected SSIS packages | DBA
30 |  |  | Notify Testers of required availability | DBA |  |  | Make sure Business Testers will be available on upgrade day.
31 |  |  | Identify IT staff to help on the upgrade
32 |  |  | Assemble the Developer support Team | DBA |  |  | Identify Developers who are familiar with the application, who will do any configuration and initial testing after the upgrade.
33 |  |  | Assemble the Network support Team | DBA |  |  | Identify Network staff who will help with O/S installs, server configurations, and backups.
34 |  |  | Database Preparation |  |  |  | For SQL 2005, refer to this article- http://msdn.microsoft.com/en-us/library/ms144245.aspx For SQL Server 2008, refer to this article - http://msdn.microsoft.com/en-us/library/ms144267.aspx
35 |  |  | Run SQL Server upgrade advisor | DBA |  |  | Review article for details on upgrade advisor- http://msdn.microsoft.com/en-us/library/ms144256.aspx
36 |  |  | Create a folder structure on a remote location to store scripts, SSIS / DTS packages, documentation, install instructions, and anything else related to the upgrade. | DBA |  |  | This should be stored in a remote location, not on the server you plan to replace or upgrade.
37 |  |  | Script Logins | DBA |  |  | Save in the Login folder http://support.microsoft.com/kb/918992
38 |  |  | Script SQL Agent jobs | DBA |  |  | Save in the Jobs folder
39 |  |  | Script Alerts | DBA |  |  | Save in the Alerts folder
40 |  |  | Script Operators | DBA |  |  | Save in the Operators folder
41 |  |  | Note Remote Server information | DBA |  |  | Document the connection configuration and place in the remote folder
42 |  |  | Script and document Linked Server information | DBA |  |  | Document the linked server configuration. Script out the linked servers into the linked Server folder
43 |  |  | Save DTS packages off to another location | DBA |  |  | DTS Designer/ Save AS - Save in the DTS folder
44 |  |  | Save SSIS packages off to another location | DBA |  |  | Save in the SSIS folder
45 |  |  | Document Maintenance plans | DBA |  |  | Save Maintenance plan documentation in the Maintenance plan folder. Print screens of maintenance plans are helpful.
46 |  |  | Document SQL Mail configuration | DBA |  |  | Save SQL Mail documentation in the SQL Mail folder.
47 |  |  | Script custom system database objects (master, msdb, model) | DBA |  |  | At some point, modifications to system data objects may have occurred, or a view, stored proc, or some other database object may have been added. Save these in the implementation plan database folder
48 |  |  | Export data and tables out of system databases (master, msdb, model) | DBA |  |  | At some point, a table may have been created in the system databases. Save these in the implementation plan database folder
49 |  |  | Script User Databases | DBA |  |  | Script the databases and save them to a database folder identified by their name.
50 |  |  | Other Services Preparation | DBA
51 |  |  | Reporting Services Preparation | DBA |  |  | Create setup and configuration documentation for Reporting Services and enter the location of the documentation in this cell. Review article for detailed steps: http://msdn.microsoft.com/en-us/library/ms143724.aspx
52 |  |  | Upgrade and modify reporting services reports | Developer
53 |  |  | Note any custom changes to reporting services configuration files | DBA
54 |  |  | Backup Configuration files for reporting services | DBA
55 |  |  | Determine if ASP.net has been encrypted in the machine.config file | DBA
56 |  |  | Back up the Symmetric encryption key (Reporting Services Configuration Tool) | DBA |  |  | Reporting Services Configuration tool or the rskeymgmt utility.
57 |  |  | Analysis Services Preparation | DBA |  |  | Create setup and configuration documentation for Analysis Services and enter the location of the documentation in this cell. Review Article for detailed steps: http://msdn.microsoft.com/en-us/library/ms143686.aspx
58 |  |  | Enter any other steps needed to prep for a Analysis Services environment | DBA
59 |  |  | Enter any other steps needed to prep for a Analysis Services environment | DBA
60 |  |  | Replication Preparation | DBA |  |  | Create setup and configuration documentation for Replication and enter the location of the documentation in this cell. Review article for detailed steps: http://msdn.microsoft.com/en-us/library/ms143699.aspx
61 |  |  | Script Replication components - Publisher / Subscriber / Snapshot | DBA
62 |  |  | Enter any other steps needed to prep for a replication environment | DBA
63 |  |  | Mirroring Preparation | DBA |  |  | Create setup and configuration documentation for Mirroring and enter the location of the documentation in this cell. Review article for detailed steps:http://msdn.microsoft.com/en-us/library/ms190941(SQL.90).aspx
64 |  |  | Verify the same supporting applications are on the principal and mirror | DBA
65 |  |  | Enter any other steps needed to prep for a mirroring environment | DBA
66 |  |  | SSIS / DTS / Application Preparation | DBA |  |  | Review article for detailed steps: http://msdn.microsoft.com/en-us/library/ms143501.aspx
67 |  |  | Create a list of which DTS packages you will migrate to SSIS and run the migration wizard. | DBA |  |  | To Migrate DTS to SSIS refer to article - http://msdn.microsoft.com/en-us/library/ms143496.aspx
68 |  |  | Create a list of which DTS packages that will remain DTS packages on the upgraded server. | DBA
69 |  |  | Modify any DTS or SSIS connections or configuration that need modified and save to a different folder than the unmodified DTS and SSIS packages. | DBA |  |  | When moving to a new server, sometimes connections and other configurations need changed.

## Upgrade Day
Step | Date | Time | Task Description | Responsible | Status | Completed | Comments
|  |  | UPGRADE DAY |  |  | Date
1 |  |  | Testing Preparation
2 |  |  | Capture Sample Test Data | Business Unit |  |  | Business Testers should capture data to perform their tests after the upgrade. This can be screen prints or other documentation.
3 |  |  | Prep for Upgrade
4 |  |  | Verify that all sql agent jobs are complete | DBA |  |  | Verify that all sql jobs are complete
5 |  |  | Verify Replication jobs are complete |  |  |  | This step is only applicable in a replication environment
6 |  |  | Kill any existing sessions | DBA |  |  | If there are any users that are still on the system, kill their session.
7 |  |  | Set all databases to Single-user or admin-only access mode | DBA |  |  | Set them to admin-only mode
8 |  |  | Create Database Count Scripts | DBA |  |  | Using Select Count(*) from [Table], count the records in your major tables.
9 |  |  | Database Backups
10 |  |  | Start full backup on all databases | DBA |  |  | Backup your databases to a secure location off the server.
11 |  |  | Stop SQL Server Agent | DBA |  |  | Stop the SQL Agent after the backups, so that no other jobs will start.
12 |  |  | Network Staff
13 |  |  | Backup Server - Databases, File Structure, etc. | Network Engineer |  |  | Get a complete backup of your system
14 |  |  | Install O/S and any other network component | Network Engineer |  |  | If upgrading the O/S, perform this step, otherwise go to the next step.
15 |  |  | Install Internet Information Services (IIS) | Network Staff |  |  | Network Staff installs IIS or any other necessary component.
16 |  |  | Do any other Server Configuration Changes | Network Staff |  |  | Network Staff performs any other O/S configuration.
17 |  |  | Upgrade SQL Server | DBA
18 |  |  | 1. Copy the SQL Server 2005 "Server" folder to your hard drive | DBA |  |  | Make Directory C:\SQLServer2005\Server
19 |  |  | 1. Copy the SQL Server 2005 "Tools" folder to your hard drive | DBA |  |  | Make Directory C:\SQLServer2005\Tools
20 |  |  | 3. Run Install from Hard Drive | DBA
21 |  |  | 4. Specify a service account that you want each component to run under | DBA |  |  | Determine which accounts you want each SQL Server Service to run under.
22 |  |  | Install Feature Pack |  |  |  | Link to the location of the feature pack.
23 |  |  | MSXML6_x86.msi | DBA |  |  | Microsoft Core XML Services (MSXML) 6.0
24 |  |  | sqlncli_x86.msi | DBA |  |  | Microsoft SQL Server Native Client
25 |  |  | SQLServer2005_xmo_x86.msi | DBA |  |  | Microsoft SQL Server 2005 Management Objects Collection
26 |  |  | SQLServer2005_BC_x86.msi | DBA |  |  | Microsoft SQL Server 2005 Backward Compatibility Components
27 |  |  | SQLServer2005_DTS.msi | DBA |  |  | Microsoft SQL Server 2000 DTS Designer Components SQLServer2005_DTS (32 bit)
28 |  |  | SQLServer2005_ASOLEDB9_x86.msi | DBA |  |  | Microsoft SQL Server 2005 Analysis Services 90 OLE DB Provider SQLServer2005_ASOLEDB9_x86
29 |  |  | SQLServer2005_SQLCMD_x86.msi | DBA |  |  | Microsoft SQL Server 2005 Command Line Query Utility SQLServer2005_SQLCMD_x86
30 |  |  | ptslite.exe | DBA |  |  | Microsoft SQL Server 2000 PivotTable Services
31 |  |  | SQLServer2005_PerformanceDashboard.msi | DBA |  |  | SQL Server 2005 Performance Dashboard Report
32 |  |  | SQL_BPASetup.msi | DBA |  |  | SQL Server 2005 Best Practices Analyzer
33 |  |  | Install Service Pack | DBA |  |  | Link to the location of the Service Pack
34 |  |  | Install the Service Pack | DBA |  |  | Copy to Hard Drive then run. It is faster.
35 |  |  | Install Applications and Drivers | DBA
36 |  |  | Setup ODBC Connections | DBA
37 |  |  | Specialized Configuration | DBA
38 |  |  | Enable xp_cmdShell | DBA |  |  | EXECUTE sp_configure 'show advanced options', 1 RECONFIGURE WITH OVERRIDE GO EXECUTE sp_configure 'xp_cmdshell', '1' RECONFIGURE WITH OVERRIDE go EXECUTE sp_configure 'show advanced options', 0 RECONFIGURE WITH OVERRIDE GO
39 |  |  | Surface Area Configuration | DBA
40 |  |  | Enable CLR | DBA
41 |  |  | Enable DAC | DBA
42 |  |  | Enable DatabaseMail | DBA
43 |  |  | Database Configuration Setup | DBA
44 |  |  | Change Compatibility level | DBA
45 |  |  | Setup SMTP Mail | DBA |  |  | Name of the mail server. Link to any documents to configure any settings.
46 |  |  | Setup Database Mail | DBA |  |  | Name of the mail server. Link to any documents to configure any settings.
47 |  |  | Place any custom stored procedures, views, tables, or other database objects in the Master. | DBA |  |  | Link to the location of the Master's custom database objects.
48 |  |  | Place any custom stored procedures, views, tables, or other database objects in the MSDB. | DBA |  |  | Link to the location of the MSDB's custom database objects.
49 |  |  | Setup Remote Servers and verify they can pull back data | DBA |  |  | Link to the Remote Server documentation
50 |  |  | Setup Linked Servers and verify that they can still pull back data. | DBA |  |  | Link to the Linked Server documentation
51 |  |  | Setup Maintenance Plans | DBA
52 |  |  | Remote Connection Verification | DBA
53 |  |  | Verify that linked and remote servers that connect to the upgraded server can still connect and pull back data | DBA
54 |  |  | Verify that DTS packages that connect to the upgraded server can still connect | DBA
55 |  |  | Verify that SSIS packages that connect to the upgraded server can still connect | DBA
56 |  |  | Verify that any other connection can still connect to the upgraded server. | DBA
57 |  |  | Database Verification | DBA
58 |  |  | Run an integrity check of each database | DBA |  |  | dbcc CheckDB
59 |  |  | Update Statistics on each Database | DBA |  |  | sp_updatestats
60 |  |  | Update database Usage | DBA |  |  | DBCC UPDATEUSAGE('DatabaseName')
61 |  |  | Run post-conversion count scripts | DBA
62 |  |  | Compare pre- & post-upgrade counts script results | DBA
63 |  |  | Set all databases to unrestricted access mode | DBA
64 |  |  | Integration Services Setup | DBA
65 |  |  | Place Windows Logins in the "Distributed COM Users" Windows group if not in Administrative Group | DBA |  |  | Link to the documentation to setup users in the Distributed COM Users Windows group. Refer to article: http://msdn.microsoft.com/en-us/library/aa337083.aspx
66 |  |  | In SSMS, place logins in Model with permissions of: db_dtsadmin, db_dtsltduser, and db_dtsoperator. | DBA |  |  | Link to a document that shows which users go in which group.
67 |  |  | Save DTS packages to SQL Server from the DTS directory. To verify, look under "Legacy" | DBA |  |  | Link to a document that shows which users go in which group.
68 |  |  | Save SSIS packages to SQL Server Integration Services. | DBA |  |  | Link to a document that shows which users go in which group.
69 |  |  | SSIS / DTS Verification | DBA
70 |  |  | Verify SSIS packages run successfully | DBA
71 |  |  | Verify DTS packages run successfully | DBA
72 |  |  | Reporting Services Setup | DBA |  |  | Enter the location of the ReportServices Setup document.
73 |  |  | Restore any custom changes to reporting services configuration files | DBA
74 |  |  | Restore Configuration files for reporting services | DBA
75 |  |  | Start the Reporting Services Configuration tool, and then connect to the report server instance you want to configure. | DBA |  |  | Enter the location of the ReportServices configuration document.
76 |  |  | Detailed steps to configure reporting services | DBA
77 |  |  | Restore Symmetric encryption key (Reporting Services Configuration Tool) | DBA |  |  | Reporting Services Configuration tool or the rskeymgmt utility
78 |  |  | Deploy Reports and verify they run correctly. | DBA
79 |  |  | Analysis Services Configuration | DBA |  |  | Refer to the preparation Analysis Services document created during the preparation stage.
80 |  |  | Enter detailed steps to configure Analysis Services | DBA
81 |  |  | Backup & Configure the msmdsrv.ini file | DBA
82 |  |  | Restart Analysis Services | DBA
83 |  |  | Replication Configuration | DBA |  |  | Refer to the preparation Replication document created during the preparation stage.
84 |  |  | Setup Snapshots | DBA
85 |  |  | Setup Publishers and Subscribers | DBA
86 |  |  | Configure Distributor | DBA
87 |  |  | Mirroring Configuration | DBA |  |  | Refer to the preparation Mirroring document created during the preparation stage.
88 |  |  | Set the principal's database to full recovery mode | DBA
89 |  |  | Backup principals databases for mirroring | DBA
90 |  |  | Restore the databases to the SQL Server 2005 Mirror. Use the NORECOVERY OPTION | DBA
91 |  |  | Copy all necessary objects to the Mirror. | DBA
92 |  |  | Logins | DBA
93 |  |  | Alerts | DBA
94 |  |  | Jobs | DBA
95 |  |  | DTS Packages | DBA
96 |  |  | Linked Servers | DBA
97 |  |  | Maintenance Plans | DBA
98 |  |  | Specialized SQL Scripts placed in the System Database | DBA
99 |  |  | Setup Endpoints | DBA
100 |  |  | Testing | DBA
101 |  |  | Notify Developer's that they can start testing | DBA
102 |  |  | Developer's test the Initial connectivity, databases functionality and application functionality testing | Developer
103 |  |  | Notify Business Tester's that they can start testing | DBA
104 |  |  | Business's unit testers arrive for testing | Business Tester
105 |  |  | Business User Tester's Test the Applications | Business Tester |  |  | Any issues that arise are sent to the DBA and the supporting developer to troubleshoot.
106 |  |  | Business User Tester's create documentation of a successful test and sends the documentation to the DBA. | DBA
107 |  |  | Business User Tester signs a form that states they tested their applications and they are satisfied with the results. | DBA
108 |  |  | DBA collect application-tester's results and signed off forms. | DBA
109 |  |  | Cleanup
110 |  |  | Get full backup of the databases | DBA
111 |  |  | Enable SQL Server Agent jobs | DBA
112 |  |  | Enable full backup jobs | DBA
113 |  |  | Run any scheduled jobs that were not run during the upgrade. | DBA
114 |  |  | Network Staff
115 |  |  | Full Server backup | Network Staff
116 |  |  | First Business Day Follow-up
117 |  |  | A DBA, Developer, and a Network engineer arrive at work early to field any issues as they arise. | DBA / Developer / Network Engineer

## RollBack Plan
Step | Date | Time | Task Description | Responsible | Status | Completed | Comments
Date
1 |  |  | Rollback Notification | DBA
2 |  |  | Notify all stake holders that a rollback is going to take place. | DBA |  |  | Make sure this is a group decision to rollback. Detail the reasons for the rollback in your communication.
3 |  |  | Restore the O/S configuration | Network Engineer
4 |  |  | Restore Server - Databases, File Structure, etc. | Network Engineer |  |  | Determine what the Network Engineers need to restore.
5 |  |  | Do any other Server Configuration Changes | Network Staff |  |  | Network Staff performs any other O/S configuration.
6 |  |  | Restore the Database configuration | DBA
7 |  |  | Un-install SQL Server | DBA
8 |  |  | Re-install previous version of SQL Server | DBA |  |  | Enter the location of the SQL Server install executables
9 |  |  | Re-Install Service Pack | DBA |  |  | Enter the location of the SQL Server Service packs.
10 |  |  | Reattach or Restore SQL Server Databases | DBA |  |  | Databases can be retrieved from SQL Server Backup or re-attached. Make sure each database is restored to the correct drive.
11 |  |  | Restore SQL Server System Databases | DBA
12 |  |  | Verify Database objects are present and functional | DBA
13 |  |  | Verify any custom store procedures, views, tables or other data objects are in the system tables | DBA
14 |  |  | Verify SQL Logins | DBA |  |  | If necessary, use the login scripts in the Login directory created during the upgrade preparation stage.
15 |  |  | Verify Database Users | DBA |  |  | If necessary, use the Logins scripts in the Login directory created during the upgrade preparation stage.
16 |  |  | Verify SQL Server Jobs | DBA |  |  | If necessary, run Job scripts in the script directory saved during the upgrade preparation stage.
17 |  |  | Verify Operators | DBA |  |  | If necessary, use the Operator scripts in the Operator directory saved during the upgrade preparation stage.
18 |  |  | Verify Alerts | DBA |  |  | If necessary, use the Alert scripts in the Alert directory saved during the upgrade preparation stage.
19 |  |  | Verify DTS Packages | DBA |  |  | If necessary, retrieve DTS packages from the DTS directory created during the preparation stage.
20 |  |  | Verify SSIS Packages | DBA |  |  | If necessary, retrieve SSIS packages from the SSIS directory created during the preparation stage.
21 |  |  | Verify Maintenance Plans | DBA |  |  | Setup maintenance plans. Refer to documentation in the maintenance plan directory created during the preparation stage.
22 |  |  | Verify that Remote Servers on other Servers still connect to this server | DBA |  |  | Verify the Remote Server connects to the destination. If necessary, use the documentation created in the preparation stage to setup and configure remote servers.
23 |  |  | Verify that Linked Servers on other Servers still connect to this server and pull back data | DBA |  |  | Verify the Linked Server connects to its destination and pulls back data. If necessary, use the scripts and documentation created in the preparation stage to setup and configure linked servers
24 |  |  | Setup ODBC Connections | DBA
25 |  |  | Setup SQL Mail | DBA |  |  | Enter location of SQL Mail documentation in this cell.
26 |  |  | Setup Replication: Publishers / Subscribers / Distributor | DBA |  |  | Setup if you are in a replication environment. Enter the location of the replication documentation created during the preparation stage in this cell.
27 |  |  | Setup and configure Mirroring | DBA |  |  | Setup if you are in a mirroring environment. Enter the location of the mirroring documentation created during the preperation stage
28 |  |  | Setup and configure Reporting Services | DBA |  |  | Setup if you are using Reporting Services. Enter the location of the Reporting Services documentation created during the preperation stage.
29 |  |  | Application Rollback Testing
30 |  |  | Notify Developer's that they can start testing application | DBA
31 |  |  | Developer's test the Initial connectivity, databases functionality and application functionality testing to make sure all applications worked as before. | Developer
32 |  |  | Notify Business Tester's that they can start testing | Business Tester
33 |  |  | Business's unit testers arrive for testing | Business Tester
34 |  |  | Business User Tester's Test the Applications to verify they worked as before. | Business Tester |  |  | Any issues that arise are sent to the DBA and the supporting developer to troubleshoot.
35 |  |  | Business User Tester's create documentation of a successful test and sends the documentation to the DBA. | DBA
36 |  |  | Cleanup | DBA
37 |  |  | Get full backup of the databases | DBA
38 |  |  | Enable SQL Server Agent jobs | DBA
39 |  |  | Enable full backup jobs | DBA
40 |  |  | Run any scheduled jobs that were not run during the upgrade. | DBA
41 |  |  | Network Backup | Network Staff
42 |  |  | Full Server backup | Network Staff
43 |  |  | First Business Day Follow-up
44 |  |  | A DBA, Developer, and a Network engineer arrive at work early to field any issues as they arise. | DBA / Developer / Network Engineer